## Risk log
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Status | Useful resources
1 | December 23,2019 | End user don't have any issue while using GWIS on Win10 workstation,but have issue with non-GWIS function,user don't aggree continue to upgrade Win10 | Unlikely | Low | Low | TL of SSP deliver team | Report HSBC IT team; Do some evaluation of impact scope; Push other team from non-GWIS function. | Communicate with end user to get confirm that they don't have any issue while using GWIS,but block with non-GWIS function. | Some stakeholder Analysis in progress. And some already have confirmed mail. | Open
2 | January, 4,2020 | HK Site user/IT plan to upgrade win10 in second half of the year,and for users in FRA site etc. Users/IT have not received any notifaction to upgrade Win10 | Unlikely | Medium | Medium | TL of SSP deliver team | Report HSBC IT team; | Communicate with Local IT to ask for help-if Local IT can send notifaction to user in advance. | Actively contacting HSBC IT contact point to promote. | Open
3 | January, 10,2020 | User have HWS workstation, IT trying to upgrade to Win10,have no succeed case for HWS workstations until now | Unlikely | Medium | Medium | TL of SSP deliver team | No ability to reduce likelihood. | Communicate with Local IT,and Local IT make this kind of machine an exception | Keep watching. | Open
4 | January, 15,2020 | No souce code of GWIS OCX for GWIS INAH 5 project | Unlikely | Medium | Medium | SSP deliver team | Report HSBC IT team; Evaluation impact scope; Evaluate the reconstruction plan and cost with the relevant parties | Find alternative software | Comminicated with relevant parties to discuss. | Open
5 | January, 10,2020 | Software package can not install on Win10 project for SPS/CPS | Unlikely | Medium | Medium | SSP deliver team | No ability to reduce likelihood. | Communicate and send notification to CWD3 team. |  | Open

## Severity Table
Likelihood
[5 empty] | Remote | Unlikely | Conceivabale | Likely | Nearly Certainly
|  |  | Impact | Low | Low | Low | Medium | Medium | Medium
|  |  |  | Medium | Low | Medium | Medium | High | High
|  |  |  | High | Medium | Medium | High | High | High
|  |  |  | Critical | Medium | Medium | High | High | High
Severity
Likelihood score | Description | Frequency How often might it/does it happen
1 | Remote | likelihood of occurrence < 10%
2 | Unlikely | likelihood of occurrence 11%~25%
3 | Conceivable | likelihood of occurrence 26%~50%
4 | Likely | likelihood of occurrence 51%~75%
5 | Nearly Certainly | likelihood of occurrence 76%~100%
Impact score | Description | Definition
1 | Low | Can still achieve expectations by taking intervention , deviations from key milestone < (1 day)
2 | Medium | Minor deviations from key milestone (1 ~ 3 days)
3 | High | Big deviations from key milestones (3 ~ 5 days), affecting critical paths
4 | Critical | Significant deviations from key milestones (> 2 weeks)

## Dropdowns
High
Medium
Low