## daily report
任务状态颜色块 | Pre-checking in processing | Pre-checking completed | SIT in processing | SIT completed | UAT in processing | UAT completed | Readay To Release | Release in processing | End
人员 | 负责站点 | 当前所处阶段 | 阻塞(是/否) | 阻塞原因 | 已实施解决方案 | 备注
康卫安 Alan | ?
李娟 Anna | 1.AMH CCB | UAT in processing
| 2.TWM AID | SIT completed
| 3.AMH ACA | UAT in processing
刘哲Jakson | 1.AMH CSBO | SIT completed
| 2.HASE CSBO | SIT completed
侯佳良Clark | 1.AMH APC | Release in processing
| 2.HASE CCCIS | SIT completed
| 3.AMH CCCIS | SIT completed
王德承Brown | 1.HASE RCS | SIT completed
| 2.AMIS | SIT completed
穆佳乐More | 1.HASE HCAP | UAT completed
| 2.CCAIS MYH | SIT completed
| 3.HASE APC | Readay To Release
| 4.AMH BDE | Readay To Release
| 5.HASE BDE | Readay To Release
| 6.HASE NTG | SIT completed
张璐Disa | all
弥军虎Jooho | 1.MYH CSBO | UAT completed
| 2.MYH CCCIS | SIT completed
| 3.AMH CCAIS | SIT completed
杨卓Eric | 1.MYH RND | SIT completed
| 2.MYH RAP | SIT completed
| 3.AMH CDA | SIT in processing